## Forwards Action Plan 2023-25
| HREiR Forward Action Plan: 2023-2026 | [6 empty] | Add institutional logo
Details
| Institution name: | Loughborough University |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: | 2 |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: | 2026-01-01 |  |  |  | Research staff |  | ~300 | Defined by Specialist and Supporting Academic (Research) job family.
| Institutional context: | Loughborough University is a research-intensive institution with exceptional Research Excellence Framework (REF) results. In 2021, 100% eligible staff were returned (top 30 by overall GPA) and > 90% of research submitted was classified as ‘world-leading’ or ‘internationally-excellent’: one of the largest increases in the sector since REF 2014. A new University Strategy, Creating Better Futures. Together, launched in March 2022, places significant emphasis on partnership working and research stating we will be ‘more ambitious in our research and innovation endeavour’ as one of the six core aims. A key aspect of our strategy is to create ‘an environment where interdisciplinary research and innovation teams can flourish and ensure that Loughborough University is anti-discriminatory, diverse, and inclusive’. This focus places the researcher experience and therefore the Concordat action plan, at the heart of the implementation of the University Strategy. LU's HREiR forwards-facing action plan should not be viewed as a static document. That is, it is highly likely that ongoing consultation with key stakeholders and results from CEDARS 2023 and 2025 will lead to additional actions that require a range of new methods to measure success. For example, running focus groups and pulse surveys as appropriate. |  |  |  | Postgraduate researchers |  | N/A | N/A
[6 empty] | Research and teaching staff |  | N/A | N/A
[6 empty] | Teaching-only staff |  | N/A | N/A
[6 empty] | Technicians |  | N/A | N/A
[6 empty] | Clinicians |  | N/A | N/A
[6 empty] | Professional support staff |  | N/A | N/A
[6 empty] | Other (please provide numbers and details): |  | N/A | N/A
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update (May 2023) | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECI1 | Ensure all relevant staff are aware of the Concordat. | Frequently refer to the Concordat within relevant development opportunities and communication channels (e.g. RS Bulletin, RS webpages and training). | No | August 23 and annually thereafter. | Organisational Development Research Innovation Office | At least 50% of RS answering CEDARS q51 ("How would you rate your knowledge and understanding of the following UK sector initiatives or frameworks?") q51.1 ("Concordat to Support the Career Development of Researchers") to state "I have some understanding" with less than 20% stating "I know this exists, but I don't know the detail". New opportunities for research develppment, training and resources reported in each staff bulletin. At least 50% of RS answering CEDARS q51 ("How would you rate your knowledge and understanding of the following UK sector initiatives or frameworks?") q51.4 ("European 'HR Excellence in Research' Award recognition") to state "I have some understanding of this" with less than 20% stating "I know this exists, but I don't know the detail".
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | i) Review, enhance and embed flexible working practices for all staff, ensuring that RS are included. | Yes (ECI2 i) | Aug-23 and annually thereafter | Human Resources Organisational Development | At least 70% of RS answering CEDARS q16 ("to what extent do you agree you are treated fairly in relation to...") q16.6 ("Requests for flexible working?"), q16.7 ("Maternity, paternity, adoption and parental leave?") "agree" or "strongly agree".
|  | ii) Share information on institutional policies and practices via several communication methods targeted at RS and their managers (e.g. RS Bulletin and webpages). | No | Aug-23 and annually thereafter | Schools RIO Human Resources Organisational Development | At least 70% RS and their managers to be aware of institutional policies and practices relevant to researchers as measured by a LU pulse survey.
|  | iii) Involve RS when reviewing/creating relevant institutional policies and practices. | No | Jan-24 and annually thereafter | RIO Human Resources Organisational Development | Membership of RIC and HRC to include a LURSA representative.
|  | iv) Investigate via consultation with ADRIs the level of representation of RS on key School committees regarding RI. | No | Jan-24 an annually thereafter | Human Resources Organisational Development Schools | All School-level committees regarding RI to have RS representation.
|  | v) Work towards achieving/maintaining Athena SWAN recognition in Schools. | Yes (ECI2 ii) | Apr-23 - Apr-26 (dependent on individual School cycles) | Schools Planning Office | Schools that currently hold an award to successfully renew by the following the dates: . -ABCE = Apr-23 -DCA = Apr-23 -Science = Nov-24 -SSH = Nov-24 -SSEHS = April-25 -MEME = Nov-25 -AACME = Apr-26 Schools that do not hold an award to do so by the following dates: -LBS = Apr-25 -LUL = Apr-23
|  | vi) Work towards renewing the University’s Athena SWAN Award. | No | 2023-04-01 | Planning Office and others from across the institution | LU to successfully renew its Athena SWAN award in 2023.
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Take part in CEDARS in 2023 and 2025, conduct LU pulse surveys/focus groups, review LU-wide staff experience surveys, and establish an efficient communication channel with LURSA. Raise outcomes with relevant services and committees as appropriate and agree interventions to address areas of concern that may arise. Establish a LU Research Culture Working Group and ensure RS representation. | No | Jan-24 and annually thereafter (NB: CEDARS will run at LU for a 3-4 week period during Mar-June 2023 and 2025) | Planning Office Organisational Development RIO Human Resources | At least 70% of RS answering CEDARS q38 ("to what extent do you agree that..." q38.1 ("You are appropriately recognised for your contributions to your institution?"), q38.2 ("Your institution promotes the highest standards of research integrity and conduct?"), q38.3 ("Your managers communicate clear expectations regarding behaviours and/or culture in my local working environment"), q38.4 ("Your institution is committed to equality and diversity?", q38.5 ("Your institution actively promotes the importance of good mental health and wellbeing of staff"), q38.6 ("Your working environment supports your mental health and wellbeing?", q39.1 ("You have a good level of job satisfaction?"), q39.2 ("You feel valued at work?"), q39.3 ("Your manager promotes a good work-life balance?"), and q39.4 ("You feel included in your immediate research environment/group?") to "agree" or "strongly agree". Research Culture Working Group established with appropriate RS representation
ECR1 |  | i) Encourage RS to attend/participate at centrally organised development and networking events targeted at RS and doctoral researchers such as LU's Annual Research Conference. Engage with LURSA and request event topic and activity suggestions that are of interest to them and doctoral researchers. | Yes (ECR1i // ECR1vi) NB: The wording of this action and success measure has changed somewhat. | Aug-23 and updated during induction events (n=4 per year) | Organisational Development RIO Schools | 100% RS notified of upcoming events targeted at early career researchers via various communication channels including the RS Bulletin. At least 10% of RS to participate at LU's Annual Research Conference. At least 5 networking events targeted at early career researchers from across LU to run on an annual basis.
|  | ii) Provide opportunities for RS to be mentored and/or become mentors. To include the creation of guidance/training of mentors, opportunities to specify any mentor/mentee preferences (i.e. from minority groups), and a review of experiences. | Yes (ECRii // ECRiii) NB: The wording of this action and success measure has changed somewhat. | Jan-24 and annually thereafter | Organisational Development RIO Schools | 100% RS provided with the opportunity to be assigned a mentor outside of their line management structure. Mentoring guidelines specifically for RS to be created and shared with mentors and researchers. To pilot with the Doctoral Prize Fellows. At least 70% of RS to agree/strongly agree that their mentoring experience has been useful as measured by pulse surveys.
|  | iii) Raise awareness of external and cross-institutional networks (such as The British Academy's Early Career Research Network, IAS, C-DICE and ERA) and encourage RS to participate. | Yes (ECR1iv // ECR1v) NB: The wording of this action and success measure has changed somewhat. | Jan-24 and annually thereafter | Organisational Development | Information on external networks and cross-institutional networks shared via various communication channels on a frequent basis (i.e. RS bulletin, webpages, training and events). More than 50% of RS to select "yes" to q58 "Have you engaged with any external or cross-institutional networks related to research careers".
Wellbeing and mental health
The aims of these obligations are to champion positive wellbeing amongst researchers, both through appropriate training and enabling new ways of working.
ECI3 | Promote good mental health and wellbeing through the effective management of workloads and people. | Promote mental health and wellbeing resources, events and initiatives via several communication channels (e.g. RS Bulletin, webpages and induction) on a rolling basis. | No | June-23 and annually thereafter | Schools Organisational Development Health & Safety | At least 70% of RS answering CEDARS q38 ("to what extent do you agree that...") q38.5 ("Your institution actively promotes the importance of good mental health and wellbeing of staff?"), q38.6 ("Your working environment supports your mental health and wellbeing?"), q39.3 ("Your manager promotes a good work-life balance?") and q49.5 ("You are encouraged to take positive action to maintain your mental health and wellbeing?") to "agree" or "strongly agree". Mental health and wellbeing resources are signposted in the RS bulletin and webpages.
ECI4 | Ensure managers of researchers are effectively trained in relation to wellbeing and mental health. | Promote LU mental health and wellbeing development sessions to managers of researchers (e.g. via School emails) on rolling basis. | No | June-23 and annually thereafter | Schools Organisational Development Health & Safety | Reduction in the number of RS complaints concerning management of mental health and wellbeing Increase of 5% in research manager engagement with mental health and wellbeing workshops/resources
ECM3 | Ensure managers promote a healthy working environment that supports researchers' wellbeing and mental health. | Explore accommodation experiences of research staff and update action plan to address any issues that arise. See also EC13 and EC14 | Yes (previously ECM3i) NB: The wording of this action and success measure has changed somewhat. | 2024-06-01 | Human Resources | Include a follow-up question to CEDARS q55 ("Did you need support in finding accommodation [when starting your role]?" and/or conduct a pulse survey/focus group to make a distinction between experiences of those who did not need and those who did need support.
ECM4 | Ensure managers consider fully flexible working requests and other appropriate arrangements to support researchers. | See EC12
ECR3 | Ensure researchers take positive action towards maintaining their wellbeing and mental health. | See EC13
Bullying and harassment
The aims of these obligations are to eliminate bullying and harassment in the research system, tackled through progressive policies and secure mechanisms to address incidents.
ECI3 | Promote a healthy working environment through effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues. | Share information on institutional policies and practices for tackling discrimination, bullying and harassment via several communication methods targeted at RS and their managers (e.g. RS Bulletin, RS webpages, training). | No | June-23 and annually thereafter | Human Resources Organisational Development Schools | At least 70% of respondents answering CEDARS q41 ("To what extend to you agree with the following statements in relation to equality and diversity?") q41.1 ("I am familiar with my institution's mechanism to report incidents of discrimination"), q41.2 ("I would feel comfortable reporting an incident of discrimination"), q41.3 ("I trust that my institution will investigate any reported incident of discrimination fairly and take appropriate action"), and q41.4 ("I think staff at my institution are treated fairly irrespective of any protected characteristics") to "agree" or "strongly agree". At least 70% of respondents answering CEDARS q42 ("To what extend to you agree with the following statements in relation to bullying and harassment?") q42.1 ("I am familiar with my institution's mechanism to report bullying or harassment"), q42.2 ("I would feel comfortable reporting an incident of bullying or harassment"), and q42.3 ("I trust that my institution will investigate any reported incident of bullying and harassment fairly and take appropriate action") to "agree" or "strongly agree". Institutional policies and practices disseminated to all RS staff and their managers.
ECM3 | Ensure managers encourage reporting and addressing incidents of discrimination, bullying and harassment. | See ECI3
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to discrimination, harassment and bullying. | See ECI3
Equality, diversity and inclusion
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and adopt practices enhancing equality, diversity and inclusion.
ECI4 / ECM1 | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work. | LU Organisational Development Hub to provide a range of optional and mandatory development opportunities (e.g. workshops and events) that focus on EDI and to raise awareness of relevant policies as appropriate. Conduct a review of completion rates of mandatory training related to EDI. | No | Jan-24 an annually thereafter | Organisational Development | In line with university-policy, 100% of staff at LU to have completed EDI-related mandatory training within 6-months of joining the University and to undertake refresher training as required. Undertake an audit on an annual basis. At least 70% of RS answering CEDARS q19 ("To what extent do you agree that your recruitment, selection and appointment process was") q19.1 ("Fair"), q19.2 ("Inclusive"), q19.3 ("Transparent"), and q19.4 ("Merit-based") to 'agree" or "strongly agree". At least 70% or respondents with management responsibilities answering CEDARS q26 ("Please indicate how confident you are in your ability to") q 26.6 ("Use inclusive, equitable and transparent recruitment processes") to feel "confident" or "fully confident". At least 70% of respondents answering CEDARS q41 ("To what extend to you agree with the following statements in relation to equality and diversity?") q41.1 ("I am familiar with my institution's mechanism to report incidents of discrimination"), q41.2 ("I would feel comfortable reporting an incident of discrimination"), q41.3 ("I trust that my institution will investigate any reported incident of discrimination fairly and take appropriate action") and 41.4 ("I think staff at my institution are treated fairly irrespective of any protected characteristics") to "agree" or "strongly agree". At least 70% of respondents answering CEDARS q38 ("To what extent do you agree that...") q38.4 ("Your institution is committed to equality and diversity") to "agree" or "strongly agree".
ECR2 | Ensure researchers act in accordance with employer and funder policies related to equality, diversity and inclusion. | See EC14 // ECM1
Research Integrity
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and maintain high standards of research integrity, and are able to report infringements or misconduct.
ECI5 / ECM2 | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. | Advertise development opportunities and resources related to research integrity and misconduct to all staff via several communication channels including the RS Bulletin and webpages. Review LU's research integrity training offering to ensure information provided to staff is up to date, high quality and meaningful. Renew LU's statement on research integrity on an annual basis and promote as appropriate. | No | Sep-23an annually thereafter | Research and Innovation Office // Organisational Development // Schools | At least 70% of respondents answering CEDARS q43 ("To what extend to you agree with the following statements in relation to research integrity?") q43.1 ("I am familiar with my institution's mechanism to report incidents of research misconduct"), q43.2 ("I would feel comfortable reporting an incident of research misconduct"), q43.3 ("I trust that my institution will investigate any reported incidents of research misconduct fairly and take appropriate action"), and q43.4 ("I trust that my institution would take action if appropriate after such an investigation") to "agree" or "strongly agree". At least 70% of respondents answering CEDARS q34("In which areas have you undertaken, or would you like to undertake, training and other continuing professional development") q34.12 ("Research integrity") to state "I have done this". At least 70% of respondents answering CEDARS q38 ("Your institution promotes the highest standards of research integrity and conduct?" to "agree" or "strongly agree". Research intergity training updated and completed by all RS related staff. All staff aware of updated Research Integrity Statement.
ECM3 | Ensure managers report and address incidents of poor research integrity. | See EC15 // ECM2
ECR2 | Ensure researchers act in accordance with employer and funder policies related to research integrity. | See EC15 // ECM2
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct. | See EC15 // ECM2
Policy development
The aims of these obligations are to encourage all researchers to actively contribute to the development of policies driving positive change at their institution.
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making. | i) Relaunch LURSA and establish a new committee/steering group with terms of reference and a transparent and fair election/selection process. | No | 2023-06-01 | Organisational Development RIO Schols | At least 10% of RS population to be a member of LURSA. To have representation from each School on the LURSA committee/steering group.
|  | ii) Invite the LURSA Committee Chair to be an official member of RIC and HRC. | No | 2023-06-01 | PVCRI Director of HR | The LURSA Committee Chair/Lead (or a suitable representative should they not be able to attend) to attend each RIC and HRC meeting and to committee key information to RS as appropriate.
|  | iii) Amend the terms of reference of RIC and HRC to include the Concordat and HREiR Award. Make 'Research Staff' a standing meeting agenda item for RIC and HRC. | No | 2023-02-01 | PVCRI Director of HR | The terms of reference of RIC and HRC to include the Concordat and the HREiR award. 'Research Staff' to be a standing agenda item in RIC and HRC meetings and for progress on the HREiR action plan to be monitored and tracked.
|  | iv) Schools to develop individual policies for RS representation at School staff meetings and relevant committees. | Yes (previously EI7i) NB: The wording of this action and success measure has changed somewhat. | 2023-06-01 | ADRIs | Each School to create a policy (and to present at RIC) to ensure that RS are represented at all relevant staff and committee meetings. At least 70% of RS answering CEDARS q14 ("To what extent to you agree that your institution treats you fairly in relation to:") q14.10 ("Opportunities to participate in decision-making processes [e.g. committees]") to "agree" or "strongly agree". At least 70% of applicable RS answering CEDARS q16 ("To what extent does your institution value the contributions that you make to" q16.6 ("Institutional policy and decision-making") to state "mostly" or "fully".
|  | v) All ADRIs to meet with RS or a LURSA-affiliated representative on a regular basis, and represent their views at relevant meetings and committees at School and/or institutional level as appropriate. | Yes (previously EI7ii) NB: The wording of this action and success measure has changed somewhat. | 2023-06-01 | ADRIs | All ADRIs (and/or others responsible for overseeing the RS-experience with Schools) to provide the opportunity to meet with RS or a LURSA-representative on a monthly-basis. Information regarding any resultant initiatives to be shared with School RS and their managers as appropriate.
ECM5 | Encourage managers to engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | Launch an ADRI Forum to meet quarterly | No | 2023-12-01 | ADRIs Organisational Development | ADRI Forum established Meeting minutes reflect impact to research environment and culture as per success measures noted in ECR1 // ECI1 // ECI2 // ECI6 // ECR1
EM5 | Engage with opportunities to contribute to relevant policy development within their institution. | See EI7
ECR5 | Encourage researchers to consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | See EI7
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community. | See EI7
Employment
Recruitment and induction
The aims of these obligations are to ensure recruitment of researchers is open and fair and researchers receive effective inductions into the organisation.
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices. | All LU staff who are planning to sit on a recruitment panel to complete LU's mandatory 'Recruitment and Selection' training and 'Unconscious Bias' training. | No | June-24 and annually thereafter | Human Resources Organisational Development Schools | 100% of LU staff who have sat on recruitment panels to have completed complete LU's mandatory 'Recruitment and Selection' training and 'Unconscious Bias' training. At least 70% of RS answering CEDARS q19 ("To what extent do you agree that your recruitment, selection and appointment process was") q19.1 ("Fair"), q19.2 ("Inclusive"), q19.3 ("Transparent"), and q19.4 ("Merit-based") to 'agree" or "strongly agree". At least 70% of respondents with management responsibilities answering CEDARS q26 ("Please indicate how confident you are in your ability to") q26.6 ("Use inclusive, equitable and transparent recruitment processes") to feel "confident" or "fully confident". At least 70% of respondents answering CEDARS q41 ("To what extend to you agree with the following statements in relation to equality and diversity?") q41.4 ("I think staff at my institution are treated fairly irrespective of any protected characteristics") to "agree" or "strongly agree".
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position. | Develop induction practices at School-level that compliment Institution-level induction practices and that are inclusive of and contain elements bespoke to RS. Recognising the variation in RS populations in Schools, each School to ensure new RS receive a formal induction process within 3 months of joining the School. Schools to monitor RS satisfaction with induction on a rolling basis and adapt practice as appropriate. | Yes NB: The wording of this action and success measure has changed somewhat. | Sep-23 and review annually thereafter | Schools Organisational Development RIO | All Schools to have induction practices that are viewed positively by attendees (as measured by School pulse surveys). 100% of RS answering CEDARS q60 ("If you have become a member of research staff at Loughborough University since June 2022, have you had an induction in your department or school that was specifically about research?") to state "yes".
Recognition, reward and promotion
The aims of these obligations are to ensure the fair and inclusive recognition of researchers as part of their career progression.
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances. | Review the recognition, reward and promotion pathways at LU to determine if they are inclusive to RS. Raise awareness of LU's reward and recognition programmes. | Yes NB: The wording of this action and success measure has changed somewhat. | Sep-24 and review annually thereafter | HR Organisational Development | At least 70% of RS answering CEDARS q14 ("To what extent do you agree that you institution treats you fairly in relation to...") q14.5 ("Career advancement opportunities") to "agree" or "strongly agree". At least 70% of RS answering CEDARS q17 ("To what extent do you agree with the following statements...") q17.1 ("The promotion pathways and processes at my institution are clear to me"), 17.2 ("My institution has equitable opportunities for career advancement"), q17.3 ("Promotions at my institutions are made on merit") to "agree" or "strongly agree". Recognition, Reward and Promotion pathways have been reviewed and disseminated across the RS community.
EM3 | Managers commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers. | See EI1 // EI3
Responsibilities and reporting
The aims of these obligations are to ensure that researchers and their managers understand and act on their obligations and responsibilities.
EM2 | Managers familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding. | Develop a training programme to ensure managers have required information. Consult with key stakeholders on content and delivery. Seek feedback on training for quality assurance/enhancement purposes. | No | 2024-06-01 | RS Managers Organisational Developoment RIO | Training completed by all managers
ER1 | Researchers ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder. | See EM2
ER2 | Researchers understand their reporting obligations and responsibilities. | See EM2
People management
The aims of these obligations are to ensure that researchers are well-managed and have effective and timely performance reviews.
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent. | Raise awareness of line and project management training opportunities for staff via various communication channels including the RS bulletin, webpages and targeted School emails. Seek feedback and review regularly for quality assurance/enhancement purposes. | No | June-23 and frequently thereafter | Organisational Development | All staff permitted to attend line and project management training opportunities. Run at least 10 sessions on the topics of line management and project management on an annual basis via Organisational Development.
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation. | Monitor PDR uptake of RS on an annual basis. See EC16 // EC12 // E13 // EM3 // EI4 | Yes NB: The wording of this action and success measure has changed somewhat. | Jan-24 and annually thereafter | Schools Human Resources Organisational Development | At least 70% of RS answering CEDARS q21("Over the past two years [or since taking up your current position if that is more recent] have you participated in staff appraisal/development review?") to state "Yes". At least 70% of RS answering CEDARS q21a ("How useful did you find your staff appraisal / development review ?") to state "useful" or "very useful". Incease of 5% of RS completing PDRs
EM1 | Managers undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care. | See E15
EM4 | Managers actively engage in regular constructive performance management with their researchers. | See E15
ER3 | Researchers positively engage with performance management discussions and reviews with their managers. | See E15
Job security
The aim of this obligation is to improve the job security of researchers.
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress. | i) Explore mechanisms to improve retention of highly skilled RS. | Yes | 2024-12-01 | PVCRI HR Organisational Development Research and Innovation Office | Report to Research Innovation Committee and HR Committee with recommendations.
|  | ii) Review redeployment policy to determine its effectiveness for retaining highly skilled RS. | Yes | 2024-12-01 | HR Organisational Development Research Staff Working Group | Report to HR Committee with recommendations for effective use of redeployment in retaining highly skilled researchers.
Professional and Career Development
Championing professional development
The aims of these obligations are to promote the importance of professional development and ensure researchers have the time to engage in it.
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors. | Review RS development needs and opportunities including those from cross-institutional and external networks as appropriate. Following consultation with key stakeholders create a new LU Researcher Development Programme of activities and events that considers a range of career aspirations and that is clearly advertised via various channels (e.g. RS Bulletin) and signposted from RS webpages, Organisational Development Hub and managers of researchers. | Yes (PDCI1 ii // PCDI1iii // PCDR3i) NB: The wording of this action and success measure has changed somewhat. | Dec-23 with an annual review | Organisational Development RIO Library Careers Network Marketing & Advancement | At least 70% of RS answering CEDARS q14 ("To what extent do you agree that your institution treats you fairly in relation to") q14.8 ("Access to training and development opportunities?") to "agree" or "strongly agree". At least 70% of RS (with/without management responsibilities) answering CEDARS q31 ("To what extent do you agree that...") q31.1 ("You manager/supervisor encourages you to engage in personal and career development activities?"), q31.2 ("Your manager/supervisor encourages you to consider a wide range of future career options within and beyond academia?), q31.3 ("You are aware of the support your institution provides for your career and professional development?"), q31.6 ("You maintain a formal record of your continuing professional development activities?") to "agree" or "strongly agree". At least 70% of RS answering CEDARS q31 ("To what extend do you agree that...") q31.7 ("You have time to develop your research identity?") and q31.8 ("You have time to develop your leadership skills?") to state "agree" or "strongly agree".
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities. | See PCDI1
PCDM3 | Managers allocate a minimum of 10 days pro rata per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development. | Create an institution-wide policy that states RS must undertake a minimum of 10 days pro rata per year professional development activities. Communicate this policy via several communication channels including targeted School emails, RS Bulletin and training sessions as appropriate. | No | July-24 with an annual review | PVCRI ADRIs RIO HR Organisational Development | 100% of pulse survey respondents to be aware of the minimum 10 day pro rata per year allocation of professional development activities. Institution policy created and disseminated.
PCDR1 | Researchers take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year. | See PCDI1 // PCDM3
Career development reviews
The aims of these obligations are to ensure researchers and their managers are engaging in productive career development reviews.
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers. | Create an institutional-wide policy that states a requirement for managers to engage in meaningful career development conversations with their researchers on a regular basis ( in addition to career conversations that take place during PDR.) See EI4 | No | July-24 with an annual review | HR | At least 70% of RS answering CEDARS q31 ("To what extent do you agree that...") q31.1 ("You manager/supervisor encourages you to engage in personal and career development activities?") and q31.2 ("Your manager/supervisor encourages you to consider a wide range of future career options within and beyond academia?) to "agree" or "strongly agree". At least 70% of RS answering CEDARS q32 ("Do you have a regular formal career development review with your manager/supervisor (separately or as part of your appraisal/performance review"?) to state "yes". At least 70% of RS answering CEDARS q32a ("How useful is the career development review with your manager/supervisor?") to state "useful" or "very useful". Institution policy created and disseminated.
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with researcher career development reviews. | See PCDI2
PCDM1 | Managers engage in regular career development discussions with their researchers, including holding a career development review at least annually. | See PCDI2
PCDR4 | Researchers positively engage in career development reviews with their managers. | See PCDI2
Career development support and planning
The aims of these obligations are to promote researchers' career development planning through tailored support and gathering evidence of professional experience.
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers. | See PCDI1
PCDR3 | Researchers maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications. | See PCDI1
Research identity and leadership
The aims of these obligations are to provide researchers with opportunity to progress in their careers by developing their research identity and leadership capabilities.
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills. | See PCDI1 // PCDI2 // PCDM3
PCDM4 | Managers identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours. | See PCDI1 // PCDI2 // PCDM3
PCDM5 | Managers engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development. | See PCDI1 // PCDI2 // PCDM3
PCDR5 | Researchers to seek out, and engage with, opportunities to develop their research identity and broader leadership skills | See PCDI1 // PCDI2 // PCDM3
Diverse careers
The aims of these obligations are to recognise, value and prepare researchers for the wide range of career options available to them within and beyond research.
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this. | See PCDI1 // PCDI2 // PCDM3
PCDM2 | Managers support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments. | See PCDI1 // PCDI2 // PCDM3
PCDR2 | Researchers explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments. | See PCDI1 // PCDI2 // PCDM3 // ECR1
PCDR6 | Researchers consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation. | See PCDI1 // PCDI2 // PCDM3
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
1 | C-DICE |  | www.cdice.ac.uk |  | ABCE | Architecture Civil and Building Engineering
2 | Dynamic Working |  | www.lboro.ac.uk/internal/dynamic-working/ |  | ADRI | Associate Dean Research and Innovation
3 | ERA |  | https://www.era.ac.uk/ |  | BAME | Black Asian and Minority Ethnic
4 | IAS |  | https://www.lboro.ac.uk/research/ias |  | C-DICE | Centre for postdoctoral development in infrastructure cities and energy
5 | Maia Network |  | https://www.lboro.ac.uk/internal/groups/maia/ |  | CEDARS | Culture, Employment and Development in Academic Research Survey
6 | Organisational Development Hub |  | www.lboro.ac.uk/services/od-hub |  | CO2RE | The Greenhouse Gas Removal Hub
7 | Loughborough University |  | www.lboro.ac.uk |  | CREDS | Centre for Research into Energy Demand Solutions
8 | Mandatory Training |  | https://www.lboro.ac.uk/services/od-hub/topics/mandatory-training/ |  | CROS | Careers in Research Online Survey
[5 empty] | EDI | Equality/Equity, Diversity and Inclusion
[5 empty] | EnergyREV | Energy Revolution programme
[5 empty] | ERA | Energy Research Accelerator
[5 empty] | HR | Human Resources
[5 empty] | IAS | Institute of Advanced Studies
[5 empty] | IDRIC | Industrial Decarbonisation Research and Innovation Centre
[5 empty] | LU | Loughborough University
[5 empty] | LURSA | Loughborough University Research Staff Association
[5 empty] | PDR | Professional Development Review
[5 empty] | PI | Principle Investigator
[5 empty] | PVCRI | Pro Vice-Chancellor Research and Innovation
[5 empty] | ResQue | Research Quality Enhancement Sub-Committee
[5 empty] | RIO | Research Innovation Office
[5 empty] | RS | Research Staff
[5 empty] | TFI Network+ | Transforming the Foundation Industries
[5 empty] | UKCCSRC | UK Carbon Capture and Storage Research Centre
[5 empty] | UKERC | UK Energy Research Centre
[5 empty] | UKRSA | UK Research Staff Association
[5 empty] | UKYA | UK Young Academy